## Sheet2
Road Map Report
| ITC - SBU1 - PBU1 - PULPMILL - CLO2 PLANT - 114320049 | [10 empty] | Print Date : 30-09-2013
From: 01-Jan-2013 To: 31-Aug-2013
| Functional Location | Category | Sub Category | Activity | Milestone | Mile Stone From Date | Mile Stone To date | Responsibility | Assigned To | Completed By | Plan Date | Actual Date | Remarks | Status
1 | BCM-FACT \ PULP MILL \DISC CHIPPER 1 - DISC CHIPPER 1 | PM | PLANNED MAINTENENCE | IDENTIFY EQUIPMENTS | VERIFY ALL EQUIPMENTS WITH SHOP FLOOR | 2013-11-01 | 2013-11-29 | N.VENKATESWARULU | K.NAGARAJU | K.NAGARAJU | 2013-11-20 | 2013-11-25 |  | COMPLETED
2 | BCM-FACT \ PULP MILL \FIBRELINE 1 - FIBRELINE 1 | SHE | SAFETY | ZERO LABOR ACCIDENTS (INCIDENT RATES) | MILESTONES | 2013-11-01 | 2013-11-07 | SK SALEEM | SK SALEEM | K.NAGARAJU | 2013-11-06 | 2013-11-07 |  | COMPLETED
3 | PBU 2 \ UTILITIES \50 TPH COAL PLANT - 50 TPH COAL PLANT | JH | CLIT | IDENTIFY CLIT STANDARDS | MILESTONE | 2013-12-01 | 2013-12-31 | T.RAMUDU | SK SALEEM | N.VENKATESWARULU | 2013-12-10 | 2013-12-18 | REMA | COMPLETED
4 | PBU BOARD \ FH - 123 \FH 123 - SHEETER 1, - FH 123 - SHEETER 1, 2 & 6 (CP) | ET | EDUCATION AND TRAINING | INCREASE TEAM EFFECTIVENESS | INCREASE TEAM EFFECTIVENESS TO 85% | 2013-11-01 | 2013-11-07 |  | K.NAGARAJU | N.VENKATESWARULU | 2013-11-01 | 2013-11-05 |  | COMPLETED